## Modules
| Main User Content | Sub-Task
1 | Expense Claim | Add Expense Claim
Delete Expense Claim
Modify Expense Claim
List All Expense Claim
2 | Employee | Add Employee
Modify Employee
List Employee
Apply Expense Claim
View Expense Claim
3 | Admin | Search Employee
Delete Employee
Project CRUD
Expense CRUD
4 | Finance Team | Approve Expense Claim
Reject Expense Claim
Show Expense Claim
5 | Project | Add Project
Modify Project
Delete Project
Display Project
Search Project
6 | Expense | Add Expense Code
Modify Expense Code
Display Expense Code
Delete Expense Code
5 | Authentication | Register
Login
Logout

## Bothra
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Employee
1.1 | Add Employee
1.1.1 | Backend | 2.5 | 3 | Monday
1.1.1 | Html Page | 3 | 2.66 | Monday
1.1.2 | Component | 1 | 1 | Monday
1.1.3 | Validations + Exception Handling | 1.5 | 1.5 | Monday
1.2 | Delete Employee
1.2.1 | BackEnd | 1 | 1 | Tuesday
1.2.2 | Html Page | 1.33 | 1.5 | Tuesday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Tuesday
1.3 | Modify Employee
1.3.1 | Html Page | 2 | 2 | Wednesday
1.3.2 | BackEnd | 1.5 | 1.5 | Wednesday
1.3.3 | Validations + Exception Handling | 1.5 | 1.5 | Wednesday
1.4 | Search Employee
1.4.1 | Html Page | 1 | 1 | Thursday
1.4.2 | BackEnd | 1 | 1.5 | Thursday
1.4.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.5 | Registration + Login + Logout
1.5.1 | Html Page | 2 | 2 | Friday
1.5.2 | BackEnd | 2 | 2 | Friday
1.5.3 | Validation | 1 | 1 | Friday
1.5.4 | Integration with backend | 1 | 1 | Friday
| Validation | 1.5 | 2 | Saturday
| Controller, Service, Backend | 2 | 1.8 | Saturday

## Anurag
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Expense
1.1 | Add Expense Code
1.1.1 | Back end | 3 | 2.5 | Monday
1.1.2 | Html Page | 1 | 1 | Monday
1.1.3 | Component | 1 | 1 | Monday
1.1.4 | Validations + Exception Handling | 2.5 | 2 | Monday
1.2 | Update Expense Code
1.2.1 | Back end | 3 | 3 | Tuesday
1.2.2 | Html Page | 1 | 1 | Tuesday
1.2.3 | Component | 1 | 1 | Tuesday
1.2.4 | Validations + Exception Handling | 2 | 1.5 | Tuesday
1.3 | Get Result
1.3.1 | Back end | 3 | 2 | Wednesday
1.3.2 | Html Page | 1 | 1 | Wednesday
1.3.3 | Component | 1 | 1 | Wednesday
1.3.4 | Validations + Exception Handling | 2 | 1.5 | Wednesday
2 | UI
2.1 | HTML / CSS
2.1.1 | Back end | 2 | 1.5 | Thursday
2.1.2 | Html Page | 1 | 1 | Thursday
2.1.3 | Component | 1 | 1 | Thursday
2.1.4 | Validations + Exception Handling | 1.5 | 1.5 | Friday
2.2 | Test Cases
2.2.1 | Back end | 2 | 2 | Friday
2.3 | Logging
2.3.1 | Logger in back end | 3 | 3 | Friday
3 | Custom Error Pages
3.1 | Html Page | 2 | 2 | Saturday
3.2 | Redirection | 3 | 2.5 | Saturday
Logger
Use Case Diagram and Front end Bootstrap
Worked on the Presentation
Exception handling.

## Pritam
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Expense Claim
1.1 | Backend
1.1 | Add Expense Claim
1.1.1 | HTML Page | 3 | 3 | Monday
1.1.2 | Component | 1 | 1 | Monday
1.1.3 | Validations + Exception Handling | 2 | 2 | Monday
1.2 | List Expense Claim
1.2.1 | HTML Page | 3 | 3 | Tuesday
1.2.2 | BackEnd | 1.5 | 1.5 | Tuesday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Tuesday
1.3 | Expense Claim access with Finance Team
1.3.1 | HTML Page | 2 | 1.5 | Wednesday
1.3.2 | BackEnd | 3 | 2 | Wednesday
1.3.3 | Validations + Exception Handling | 2 | 2 | Wednesday
2 | Cloud Deployment
2.1 | EC2, S3, RDS | 2 | 2 | Thursday
2.2 | Jack DB Setup | 1 | 1 | Thursday
2.3 | Deployment and Testing | 2 | 2 | Friday

## Panja
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Finance Team
1.1 | Documentation
1.1.1 | UCD | 0.25 | 0.25 | Saturday
1.1.2 | Sequence Diagram | 0.5 | 0.25 | Saturday
1.1.3 | Activity Diagram | 0.25 | 0.25 | Saturday
1.1.4 | Class Diagram | 0.25 | 0.25 | Saturday
1.2 | Spring Boot Application
1.2.1 | Basic Layered Architechture | 1 | 0.75 | Monday
1.2.2 | Add Finance User | 0.5 | 0.5 | Monday
1.2.3 | Update Finance User | 0.75 | 0.75 | Monday
1.2.4 | List and Update Claims | 0.5 | 0.5 | Monday
1.3 | Spring Boot Application Enhancements
1.3.1 | Validations + Exception Handling | 2 | 1.75 | Tuesday
1.3.2 | Logging | 1 | 3 | Tuesday | System Issues
1.3 | Add Finance User
1.3.1 | Html Page | 3 | 3 | Tuesday
1.3.2 | Component | 1 | 1 | Tuesday
1.3.3 | Validations + Exception Handling | 1.5 | 1.5 | Wednesday
1.4 | Update Finance User
1.4.1 | Html Page | 1 | 1 | Wednesday
1.4.2 | Component | 1 | 1.5 | Wednesday
1.4.3 | Validations + Exception Handling | 1.5 | 1.5 | Wednesday
1.5 | Modify Expense Claim
1.5.1 | Html Page | 2 | 2.5 | Thursday
1.5.2 | Component | 1.5 | 1.5 | Thursday
1.5.3 | Validations + Exception Handling | 1.5 | 1.5 | Thursday
1.6 | Registration + Login + Logout
1.6.1 | Html Page | 2 | 1.5 | Friday
1.6.2 | Component | 2 | 2 | Friday
1.6.3 | Validation | 1 | 1 | Friday
| Integration with backend | 1 | 1 | Friday
1.5.4
Validation
Controller, Service, Backend
Angular

## Zeeshan
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Project
1.1 | Project CRUD
1.1.1 | Spring Starter Project | 3 | 3 | Monday
1.1.2 | BackEnd | 1 | 1 | Monday
1.1.3 | Validations + Exception Handling | 2 | 2 | Monday
1.2 | Business Logic
1.2.1 | HTML Page | 2 | 3 | Tuesday
1.2.2 | BackEnd | 2.5 | 2.5 | Tuesday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Tuesday
1.3 | Angular Framework | 3 | 3 | Wednesday
1.3.1 | HTML Page | 1.5 | 1.5 | Wednesday
1.3.2 | BackEnd | 1.5 | 1.5 | Wednesday
1.4 | Validations + Exception Handling
1.4.1 | BackEnd | 1.5 | 1.5 | Thursday
2 | Documentation
2.1 | UML Diagram | 3 | 2 | Friday
2.2 | Presentation | 4 | 4 | Saturday
2.3 | PLP Write Up | 3 | 4 | Saturday